## Gantt-Diagramm
AAS-Webclient
Project Title |  | AAS-Webclient |  |  |  |  | Company Name
Project Manager |  | Ilir Emini |  |  |  |  | Date | [6 empty] | 2023-09-08
PSP-Nummer | Tasks | Task-Owner | Begining Date | End Date | Time | % Pecentage of finished Task | PHASE 1 | [14 empty] | PHASE 2 | [14 empty] | PHASE 3 | [14 empty] | PHASE 4
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Projectconception and -initialitation
2018-01-01 | Creation of the specifications sheet | Ay Ümmühan | 2023-10-12 | 2023-11-05 | 15 | 100% | bar: WEEK 1 M to WEEK 2 F
1.1.1 | Revision of the specifications sheet | Ay Ümmühan | 2023-11-02 | 2023-11-06 | 5 | 100% | bar: WEEK 2 M to WEEK 3 M
2018-02-01 | Creation of the Business Case | Emini Ilir, Bauer David, Sancho Pernas Rafael | 2023-10-14 | 2023-11-05 | 15 | 100% | bar: WEEK 2 M to WEEK 3 T
2023-03-01 | Risk Analysis | Bauer David | 2023-10-15 | 2023-11-05 | 5 | 100% | bar: WEEK 1 W to WEEK 2 T
2023-04-01 | Create as-is analysis | Ay Ümmühan | 2023-10-16 | 2023-11-02 | 5 | 100% | bar: WEEK 1 F to WEEK 2 W
2023-05-01 | Create architecture specifications sheet | Lorke Lara, Taktar Armin | 2023-10-18 | 2023-11-10 | 10 | 100%
2023-06-01 | Create system test plan | Zieher Kyle | 2023-10-19 | 2023-11-11 | 5 | 100%
2023-07-01 | Create Time Scedule | Emini Ilir, Bauer David, Sancho Pernas Rafael | 2023-10-13 | 2023-10-27 | 5 | 70% | bar: WEEK 1 W to WEEK 2 F
2023-08-01 | Wiki | Ay Ümmühan | 2023-10-12 | 2023-11-15 | 20 | 50% | bar: WEEK 1 M to WEEK 4 T
2 | Developmentphase
2018-01-02 | Adoption of predecessor project | Alle | 2023-10-16 | 2023-10-20 | 5 | 80% | bar: WEEK 4 F to WEEK 5 W
2018-02-02 | GUI Updates implementation | Alle | 2023-10-23 | 2023-11-30 | 20 | 10% | bar: WEEK 5 M to WEEK 8 T
2018-03-02 | Default/Expert Mode implementation | Alle | 2023-11-10 | 2023-12-10 | 5 | 0% | bar: WEEK 6 T to WEEK 8 F
2018-04-02 | Name Plate Generator-API implementation | Alle | 2023-11-05 | 2023-12-12 | 10 | 0% | bar: WEEK 6 F to WEEK 9 T
3 | Bugfixing und Maintenance
2018-01-03 | Tests/Troubeshooting | Zieher Kyle, Alle | 2023-11-30 | 2023-12-15 | 15 | 0% | bar: WEEK 9 M to WEEK 11 W
2001-01-03 | System test reports | Zieher Kyle, Alle | 2023-12-04 | 2023-12-07 | 5 | 0% | bar: WEEK 9 T to WEEK 10 M
2018-02-03 | User-Manuel | Ay Ümmühan | 2023-11-30 | 2023-12-14 | 5 | 0% | bar: WEEK 8 T to WEEK 11 T
3.3 | Submodells hierarchial Structures supp. | Alle | 2023-11-30 | 2023-12-05 | 15 | 0% | bar: WEEK 8 F to WEEK 11 T
3.4 | GitHub-Hosting | Emini Ilir | 2023-12-14 | 2023-12-18 | 5 | 0% | bar: WEEK 9 T to WEEK 10 F
2023-05-03 | Module | Alle | 2023-12-03 | 2023-12-12 | 10 | 0% | bar: WEEK 9 T to WEEK 11 M
4 | Projectresult and Survailance
2018-01-04 | Project Goals | Emini Ilir | 2023-10-12 | 2024-01-05 | 0 | 5%
2018-02-04 | Quality Ensurance | Bauer David | 2023-10-12 | 2024-01-05 | 0 | 5%
2018-03-04 | Effort and cost monitoring | Emini Ilir | 2023-10-12 | 2024-01-05 | 0 | 5%
2018-04-04 | Project Results | Alle | 2023-10-12 | 2024-01-05 | 0 | 5%